## Sheet1 (2)
Week | Mon | Tue | Wed | Thu | Fri | SUNDAY | Project | Start | End | Topic
2016-04-25 | [5 empty] | 2016-05-01 | Mxnet Demo | 2016-04-25 | 2016-05-01 | Read documents. Get familiar with details of code structure for neural network symbol.
2016-05-02 | [5 empty] | 2016-05-08 | MXNet Demo | 2016-05-02 | 2016-05-08 | Read documents. Get familiar with details of code structure of tensor computation in mxnet so that I could better adapt my RNN codes for appropriate forward/backward propagation.
2016-05-09 | [6 empty] | NYU Final | 2016-05-09 | 2016-05-16 | NYU Final exam season.
2016-05-16 |  | 2016-05-17 |  |  |  | 2016-05-22 | Contact Mentor | 2016-05-17 | 2016-05-22 | Contact with mentors to get started. Set up formal communication tools e.g. Gitter.
2016-05-23 | START | [5 empty] | RNN Many-to-Many
2016-05-30 | [5 empty] | 2016-06-05
2016-06-06 | [6 empty] | RNN 1-to-N
2016-06-13 |  |  |  | 2016-06-16 | 2016-06-17 |  | RNN N-to-1
2016-06-20 | [5 empty] | 2016-06-26
2016-06-27 | [6 empty] | RNN N-to-N
2016-07-04 |  | 2016-07-05 | 2016-07-06 |  |  |  | Bi-RNN
2016-07-11 |  |  |  | 2016-07-14 | 2016-07-15 |  | Stack-RNN
2016-07-18 | [5 empty] | 2016-07-24
2016-07-25 | [6 empty] | LSTM
2016-08-01 | [5 empty] | 2016-08-07
2016-08-08 |  |  | 2016-08-10 | 2016-08-11 |  | 2016-08-14 | GRU
2016-08-15 | [5 empty] | 2016-08-21 | Appication
2016-08-22 | Doc (Ends) | END | Eval | Eval | Eval | Eval | Final Eval
2016-08-29 | SUBMIT
Start | End | APIs | Demo | Days
2016-05-23 | 2016-06-05 | Synced Many2Many | Binary Addition | 12
2016-06-06 | 2016-06-16 | One2Many | Image Classification | 10
2016-06-17 | 2016-06-26 | Many2One | Char RNN | 8
2016-06-27 | 2016-07-05 | Many2Many | Translation English to French | 8
2016-07-06 | 2016-07-14 | Bidirectional | Translation English to French | 8
2016-07-15 | 2016-07-24 | Stacked | Translation English to French | 8
2016-07-25 | 2016-08-10 | LSTM and GRU | Char RNN | 15
2016-08-11 | 2016-08-21 | Cbio App | Nature | 9
Formulas:
Week = DATE(YEAR([Week, row below]),MONTH([Week, row below]),DAY([Week, row below])-7)
Week = DATE(YEAR([Week, row above]),MONTH([Week, row above]),DAY([Week, row above])+7)
SUNDAY = [Week, row below]-1
Start = [Week]
Start = [Tue]
End = [SUNDAY]
End = [Week, row below]
Tue = [Week]+1
Thu = [Week]+3
Thu = [Wed]+1
Fri = [Thu]+1
Wed = [Tue]+1
Wed = [Week]+2

## Sheet1
Week | Mon | Tue | Wed | Thu | Fri | Sat | Project
2016-05-02 | [6 empty] | MXNet Demo
2016-05-09 | [6 empty] | Paper Reading
2016-05-16 | [6 empty] | Contact Mentor
2016-05-23 | Code (Starts) | Code | Code | Code | Test | Doc | RNN Many-to-Many
2016-05-30 | Code | Code | Test | Code | Code | Doc (Ends) | ditto
2016-06-06 | Code (Starts) | Code | Code | Code | Test | Doc (Ends) | RNN 1-to-N
2016-06-13 | Code (Starts) | Code | Code | Code | Test | Doc (Ends) | RNN N-to-1
2016-06-20 | Eval | Code (Starts) | Code | Code | Test | Doc (Ends) | RNN N-to-N
2016-06-27 | Doc | Doc (Starts) | Code | Code | Code | Code | Bi-RNN
2016-07-04 | Test | Doc (Ends) | Code (Starts) | Code | Code | Code | Stack-RNN
2016-07-11 | Test | Doc (Ends) | Code (Starts) | Code | Code | Code | LSTM
2016-07-18 | Test | Doc (Ends) | Code (Starts) | Code | Code | Code | GRU
2016-07-25 | Test | Doc (Ends) | Contact | Code (Starts) | Code | Code | Application
2016-08-01 | Code | Test (Ends) | Contact | Doc (Starts) | Code | Code | R-language specific domain
2016-08-08 | Code | Code | Test | Doc | Code | Code | ditto
2016-08-15 | Code | Code | Test | Doc (Ends) | Test (Starts) | Test | Wrap
2016-08-22 | Doc (Ends) | END | Eval | Eval | Eval | Eval | Final Eval
2016-08-29 | SUBMIT
Formulas:
Week = DATE(YEAR([Week, row below]),MONTH([Week, row below]),DAY([Week, row below])-7)
Week = DATE(YEAR([Week, row above]),MONTH([Week, row above]),DAY([Week, row above])+7)

## Sheet2
Date | Event | Media | Days after establishment of idea
2016-02-17 | MXNet initiated idea page on rstats-GSoC | NA | 0
2016-02-24 | Finished a proof-of-concept of RNN implemented in Rcpp and contact mentors | Github | 7
2016-03-02 | Submitted "Pull Request" as qualification of mentor test | Github | 14
2016-03-02 | Contact mentors to express my interest in MXNet's GSoC project | Email | 14
2016-03-03 | My PR being merged | Github | 15
2016-03-08 | First draft of student application form | Email&Github | 20
2016-03-10 | Second draft of student application form | Github | 22